## Start here
Data Governance Starter Kit
What this is | A set of fill-in templates to help you start a data governance program on one domain — the companion to the article “Where to begin with data governance.”
How to use it | Work through the tabs in order. Each maps to a step in the article. Start narrow: one domain, real names, a few enforceable policies, and a visible win.
Tab 1 · Domain Scoping | Pick one domain and draw a hard boundary around it.
Tab 2 · Ownership & Stewardship | Name the people accountable for the data — before you buy tools.
Tab 3 · Policy Register | A few policies you will actually enforce, each tied to evidence.
Tab 4 · Gap Log | Track what isn’t governed yet, by severity and owner.
Tab 5 · 90-Day Plan | A first-quarter shape; the audit-ready baseline is the ~30-day milestone.
Tab 6 · Scorecard | The few outcome measures worth reporting to leadership.
Legend | Cells shaded yellow are for you to fill in. The grey italic row in each tab is an example — replace or delete it.
From | Procela · procela.ai/resources/blog

## 1. Domain Scoping
Domain Scoping
Scope ONE high-value domain — the one behind a problem the business already feels. If the systems list runs past a page, cut it down.
Domain name |  | e.g., Customer Billing
Business problem it addresses |  | e.g., Monthly revenue report nobody trusts
Executive sponsor |  | e.g., VP Finance
Target baseline date |  | e.g., 30 days from kickoff
System / source | Type | Data it holds | In scope? (Y/N) | Notes
Billing Engine | Application DB | Invoices, charges | Y | Primary source

## 2. Ownership & Stewardship
Ownership & Stewardship
Name real people who answer for the data. Empty cells are your first finding, not a failure.
Data area / asset | Domain | Owner (accountable) | Steward (day-to-day) | Backup | Notes
Customer Master | Customer Billing | A. Ford (Dir, Billing) | D. Chang (Analyst) | P. Rao | Owner confirmed 9/26

## 3. Policy Register
Policy Register
A few policies you will ACTUALLY enforce. If you can’t name who enforces it and how you’d prove it, it’s an aspiration — not a policy.
Policy | Domain / scope | Type (Access/Retention/Classification/Other) | Enforced by (system / process) | Evidence (how you prove it) | Status (Draft/Active/Not enforced)
PII access restricted to Billing team | Customer Billing | Access | IAM group + quarterly review | Access review export | Active

## 4. Gap Log
Gap Log
What isn’t governed yet. Rank by where it actually hurts — a gap on data feeding a regulator is not the same as one on a scratch table.
Gap | Category | Severity (High/Med/Low) | Owner | Identified | Target date | Status (Open/In progress/Closed)
Billing Records unclassified | Classification | High | D. Chang | 2026-09-01 | 2026-09-20 | In progress

## 5. 90-Day Plan
90-Day Plan
A first-quarter shape — adapt it. The audit-ready baseline is the ~30-day milestone, not the finish line; the rest is momentum.
Phase | Weeks | Milestone | Owner | Status | Notes
Frame | 1–2 | Name the problem and the sponsor; pick one domain
Map | 3–6 | Map the domain’s systems and data; assign owners and stewards
Govern | 7–10 | Write and wire up two or three policies; surface the obvious gaps
Expand | 11–13 | Close a visible gap; report the one number; plan domain two
Milestone: an audit-ready baseline on the domain often lands ~30 days in — catalog, classify, assign owners, record controls. Treat it as the first milestone.

## 6. Scorecard
Governance Scorecard
The few outcome measures worth reporting to leadership. Each needs a target, an owner, and a source. Five numbers beat forty charts.
Measure | What it means | Target | Current | Prev / trend | Owner | Source
Coverage of critical data | Share of highest-tier assets with an owner, a classification, and a policy
Classification of sensitive data | How much regulated / sensitive data is actually labeled
Ownership | Share of key domains and assets with a named, current owner
Open issues | Unresolved governance issues, and how long they’ve been open
Exceptions | Approved policy exceptions, and how many are past their review date